## Product Backlog
Planned Sprint | Actual Sprint | US ID | User Story Description | MOSCOW | Dependency | Assignee | Status
S1 | S1 | US-001 | Setup Spring Boot project and development environment | MUST HAVE | No Dependency | Guru Sharan K | 3- Completed
S1 | S1 | US-002 | Configure project dependencies and initial backend setup | MUST HAVE | Maven | Guru Sharan K | 3- Completed
S2 | S2 | US-003 | Design database schema and create TestCase entity | MUST HAVE | MySQL | Guru Sharan K | 3- Completed
S2 | S2 | US-004 | Implement JPA repository for database operations | MUST HAVE | JPAS | Guru Sharan K | 3- Completed
S3 | S3 | US-005 | Develop REST APIs for test case creation and retrieval | MUST HAVE | Spring Boot | Guru Sharan K | 3- Completed
S3 | S3 | US-006 | Implement service layer for business logic handling | MUST HAVE | JAVA | Guru Sharan K | 3- Completed
S4 | S4 | US-007 | Integrate REST-Assured for API automation testing | MUST HAVE | REST-Assured | Guru Sharan K | 3- Completed
S4 | S4 | US-008 | Implement API test execution and validation logic | MUST HAVE | HTTP APIs | Guru Sharan K | 3- Completed
S5 | S5 | US-009 | Integrate Selenium WebDriver for UI automation testing | MUST HAVE | Selenium | Guru Sharan K | 3- Completed
S5 | S5 | US-010 | Implement UI test execution using browser automation | MUST HAVE | ChromeDriver | Guru Sharan K | 3- Completed
S6 | S6 | US-011 | Implement UI test execution using browser automation | MUST HAVE | JAVA | Guru Sharan K | 3- Completed
S6 | S6 | US-012 | Implement dynamic test execution based on test type | MUST HAVE | Backend Logic | Guru Sharan K | 3- Completed
S7 | S7 | US-013 | Implement failure handling mechanism for test cases | MUST HAVE | Execution Engine | Guru Sharan K | 3- Completed
S7 | S7 | US-014 | Add screenshot capture for failed UI tests | MUST HAVE | Selenium | Guru Sharan K | 3- Completed
S8 | S8 | US-015 | Store execution results and test history in database | MUST HAVE | MySQL | Guru Sharan K | 3- Completed
S8 | S8 | US-016 | Develop APIs to fetch execution results and summaries | MUST HAVE | REST APIs | Guru Sharan K | 3- Completed
S9 | S9 | US-017 | Implement reporting system (logs and summaries) | SHOULD HAVE | Logging | Guru Sharan K | 3- Completed
S9 | S9 | US-018 | Improve logging and debugging for test execution | SHOULD HAVE | Logger | Guru Sharan K | 3- Completed
S10 | S10 | US-019 | Develop analytics features for test results visualization | SHOULD HAVE | Backend APIs | Guru Sharan K | 3- Completed
S10 | S10 | US-020 | Final system testing, debugging, and integration | MUST HAVE | Full System | Guru Sharan K | 3- Completed
Note on F1: ====== ID#AAABcShYZQo Sumeet Kumar Barua08 (2025-01-27 09:44:41) Mention the US ID(s) on which the user story depends.

## Sprint Backlog
NOTES: Task sizing should be between 0.5 to 12 hours
US ID | Task ID | Task Description | Task Start Date | Task Completion Date | Team Member | Activity | Status | Original Estimate Effort (In Hours) | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9 | Day 10 | Day 11 | Day 12 | Day 13 | Day 14 | Day 15 | Day 16 | Day 17 | Day 18 | Day 19 | Day 20 | Day 21 | Day 22 | Day 23 | Day 24 | Day 25 | Day 26 | Day 27 | Day 28 | Day 29 | Day 30 | Day 31 | Day 32 | Day 33 | Day 34 | Day 35 | Day 36 | Day 37 | Day 38 | Day 39 | Day 40 | Day 41 | Day 42 | Day 43 | Day 44 | Day 45 | Day 46 | Day 47 | Day 48 | Day 49 | Day 50 | Day 51 | Day 52 | Day 53 | Day 54 | Day 55 | Day 56
[8 empty] | 120 | 11 | 8 | 6 | 5 | 4 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 26 | 0 | 94 | 4 | 0 | 0 | 1 | 1 | 0 | 29 | 5 | 6 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 4 | 0 | 0
SPRINT 1 (Days 1–14) – Foundation | bar: Day 1 to Day 14
US ID | Task ID | Task Description | Start Date | End Date | Team Member | Activity | Status | Effort | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-001 | 1 | Setup Spring Boot project and environment | 2025-02-25 | 2025-02-26 | Guru Sharan K | Setup | 3- Completed | 3 | 3 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-002 | 2 | Configure dependencies and project structure | 2025-02-27 | 2025-02-28 | Guru Sharan K | Setup | 3- Completed | 4 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-003 | 3 | Design database schema (TestCase entity) | 2025-03-01 | 2025-03-02 | Guru Sharan K | Design | 3- Completed | 4 | 2 | 2 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-004 | 4 | Implement JPA repository | 2025-03-03 | 2025-03-04 | Guru Sharan K | Coding | 3- Completed | 5 | 1 | 1 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-005 | 5 | Develop REST APIs (GET/POST) | 2025-03-05 | 2025-03-07 | Guru Sharan K | Coding | 3- Completed | 6 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-006 | 6 | Test APIs using Postman | 2025-03-08 | 2025-03-10 | Guru Sharan K | Testing | 3- Completed | 4 | 2 | 2 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
SPRINT 2 (Days 15–28 → 11 Mar – 24 Mar)
[23 empty] | US ID | Task ID | Task Description | Start Date | End Date | Team Member | Activity | Status | Effort
[23 empty] | US-007 | 7 | Integrate REST-Assured for API testing | 2025-03-11 | 2025-03-12 | Guru Sharan K | Integration | 3- Completed | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[23 empty] | US-008 | 8 | Develop API execution logic | 2025-03-13 | 2025-03-15 | Guru Sharan K | Coding | 3- Completed | 6 | 0 | 0 | 0 | 2 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[23 empty] | US-009 | 9 | Validate API responses | 2025-03-16 | 2025-03-17 | Guru Sharan K | Testing | 3- Completed | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[23 empty] | US-010 | 10 | Connect execution engine with backend | 2025-03-18 | 2025-03-20 | Guru Sharan K | Coding | 3- Completed | 6 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[23 empty] | US-011 | 11 | Implement logging for API execution | 2025-03-21 | 2025-03-22 | Guru Sharan K | Enhancement | 3- Completed | 3 | 0 | 0 | 0 | 2 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[23 empty] | US-012 | 12 | Debug API issues and fix errors | 2025-03-23 | 2025-03-24 | Guru Sharan K | Debugging | 3- Completed | 4 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
SPRINT 3 (Days 29–42 → 25 Mar – 07 Apr)
[32 empty] | US ID | Task ID | Task Description | Start Date | End Date | Team Member | Activity | Status | Effort
[32 empty] | US-013 | 13 | Integrate Selenium WebDriver | 2025-03-25 | 2025-03-26 | Guru Sharan K | Integration | 3- Completed | 4 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[32 empty] | US-014 | 14 | Implement browser automation logic | 2025-03-27 | 2025-03-29 | Guru Sharan K | Coding | 3- Completed | 6 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[32 empty] | US-015 | 15 | Add dynamic execution (UI/API) | 2025-03-30 | 2025-04-01 | Guru Sharan K | Coding | 3- Completed | 6 | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[32 empty] | US-016 | 16 | Develop execution engine | 2025-04-02 | 2025-04-04 | Guru Sharan K | Coding | 3- Completed | 6 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[32 empty] | US-017 | 17 | Implement failure detection logic | 2025-04-05 | 2025-04-06 | Guru Sharan K | Testing | 3- Completed | 4 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[32 empty] | US-018 | 18 | Add screenshot capture for failures | 2025-04-07 | 2025-04-07 | Guru Sharan K | Debugging | 3- Completed | 3 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
SPRINT 4 (Days 43–56
[51 empty] | US ID | Task ID | Task Description | Start Date | End Date | Team Member | Activity | Status | Effort
[51 empty] | US-019 | 19 | Store execution results in database | 2025-04-08 | 2025-04-10 | Guru Sharan K | Coding | 3- Completed | 5 | 0 | 0 | 0 | 0 | 0
[51 empty] | US-020 | 20 | Develop result APIs | 2025-04-11 | 2025-04-12 | Guru Sharan K | Coding | 3- Completed | 4 | 1 | 0 | 1 | 0 | 0
[51 empty] | US-021 | 21 | Implement reporting system | 2025-04-13 | 2025-04-15 | Guru Sharan K | Coding | 3- Completed | 5 | 0 | 2 | 1 | 0 | 0
[51 empty] | US-022 | 22 | Improve logging and traceability | 2025-04-16 | 2025-04-17 | Guru Sharan K | Enhancement | 3- Completed | 4 | 1 | 1 | 2 | 0 | 0
[51 empty] | US-023 | 23 | Develop analytics features | 2025-04-18 | 2025-04-19 | Guru Sharan K | Coding | 3- Completed | 4 | 1 | 2 | 0 | 0 | 0
[51 empty] | US-024 | 24 | Final testing and debugging | 2025-04-20 | 2025-04-21 | Guru Sharan K | Testing | 3- Completed | 5 | 0 | 0 | 0 | 0 | 0
Note on D2: ====== ID#AAABcShYZRI Please enter the dates in either of these formats (2025-01-27 09:44:41) 9/15/2016 or 15-Sep-2016
Note on E2: ====== ID#AAABcShYZRU Please enter the dates in either of these formats (2025-01-27 09:44:41) 9/15/2016 or 15-Sep-2016
Note on I3: ====== ID#AAABcShYZQ4 Sumeet Kumar Barua08 (2025-01-27 09:44:41) This is the total task estimated in hours for all the user stories
Note on J3: ====== ID#AAABcShYZRc Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 1 work
Note on K3: ====== ID#AAABcShYZRg Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 2 work
Note on L3: ====== ID#AAABcShYZQs Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 3 work
Note on M3: ====== ID#AAABcShYZRo Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 4 work
Note on N3: ====== ID#AAABcShYZQw Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 5 work
Note on O3: ====== ID#AAABcShYZRk Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 6 work
Note on P3: ====== ID#AAABcShYZRY Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 7 work
Note on Q3: ====== ID#AAABcShYZRA Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 8 work
Note on R3: ====== ID#AAABcShYZRs Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 9 work
Note on S3: ====== ID#AAABcShYZRM Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 10 work
Note on T3: ====== ID#AAABcShYZRE Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 11 work
Note on U3: ====== ID#AAABcShYZQ8 Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 12 work
Note on V3: ====== ID#AAABcShYZQ0 Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 13 work
Note on W3: ====== ID#AAABcShYZRQ Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 14 work

## Stand up Meeting
Sprint | Day | Impediments | Action Taken
Sprint 1 | Day 3 | Difficulty in setting up Spring Boot environment | Reconfigured dependencies and followed official documentation
Sprint 1 | Day 5 | Issues connecting application with MySQL database | Verified DB configuration and fixed connection properties
Sprint 2 | Day 9 | Confusion in implementing REST API structure | Reviewed layered architecture and refactored controller-service flow
Sprint 2 | Day 11 | API responses not returning expected results | Debugged endpoints and validated request-response handling
Sprint 3 | Day 16 | Difficulty integrating REST-Assured with project | Studied documentation and tested APIs independently
Sprint 3 | Day 18 | Issues in Selenium WebDriver setup | Installed correct driver version and configured system path
Sprint 3 | Day 20 | Browser automation not executing properly | Debugged driver initialization and fixed execution flow
Sprint 4 | Day 25 | Test cases not updating correct PASS/FAIL status | Fixed validation logic and improved condition checks
Sprint 4 | Day 27 | Screenshot not capturing on test failure | Implemented proper exception handling and file storage logic
Sprint 4 | Day 30 | Difficulty in storing execution results in database | Updated entity mapping and verified repository logic
Sprint 5 | Day 35 | Issues in fetching execution results via API | Fixed API endpoints and response structure
Sprint 5 | Day 38 | Logs not clearly showing execution details | Improved logging format for better traceability
Sprint 6 | Day 45 | Integration issues between frontend and backend | Fixed API URLs and ensured proper request flow
Sprint 6 | Day 50 | Minor bugs during final testing phase | Performed debugging and resolved edge cases

## Retrospection
SL # | Sprint # | Sprint start date | Sprint end date | Team member name | Start Doing | Stop Doing | Continue Doing | Action taken
1 | Sprint 1 | Day 1 | Day 14 | Guru Sharan | Start planning tasks before coding | Stop random coding without structure | Continue learning fundamentals | Followed proper project structure
2 | Sprint 2 | Day 15 | Day 28 | Guru Sharan | Start writing clean APIs | Stop skipping error handling | Continue testing APIs regularly | Improved API validation logic
3 | Sprint 3 | Day 29 | Day 42 | Guru Sharan | Start integrating automation early | Stop delaying debugging tasks | Continue practicing Selenium | Fixed WebDriver and execution issues
4 | Sprint 4 | Day 43 | Day 56 | Guru Sharan | Start focusing on final testing | Stop ignoring edge cases | Continue improving test coverage | Completed system and debugging